## Excel Gantt Chart Template
DotaMatch |  |  | DUARNATION (days)
START DATE | END DATE | TASK NAME
2016-02-03 | 2016-02-17 | Project Team Selection | 14
2016-02-07 | 2016-02-10 | Brainstorm | 3
2016-02-10 | 2016-02-12 | Outline Functions of Idea | 2
2016-02-13 | 2016-02-17 | Milestone 1: Project Proposal | 4
2016-02-17 | 2016-02-20 | Outline Requirements | 3
2016-02-20 | 2016-03-07 | Systems Requirements Specificiation (SRS) Version 1.0 | 17
2016-03-07 | 2016-03-10 | Review SRS Version 1.0 | 3
2016-03-10 | 2016-03-23 | Milestone 2: Systems Requirements Specificiation (SRS) Version 2.0 | 13
2016-03-23 | 2016-04-06 | Milestone 3: Software Project Management Plan (SPMP) Version 1.0 | 13
2016-04-06 | 2016-04-11 | Milestone 4: Software Analysis Specification (SAS) Version 1.0 | 5
2016-04-11 | 2016-04-25 | Milestone 5: Software Design Document (SDD) Version 1.0 | 14
2016-05-02 | 2016-05-09 | Oral Presentation | 7

## Excel Timeline Template
Excel Timeline Template
Enter Your Project Details Here
DATE | DESCRIPTION | POSITION
2015-05-10 | Kick Off | 1
2015-06-07 | Milestone 1 | 2
2015-07-21 | Milestone 2 | 1
2015-08-01 | Checkpoint A | 4
2015-09-20 | Milestone 3 | 3
2015-10-30 | Milestone 4 | 2
2015-12-20 | Checkpoint B | 3
2016-01-30 | Milestone 5 | 4
2016-02-10 | Milestone 6 | 1
2016-03-30 | Milestone 7 | 2 |  |  | `
2016-05-20 | Checkpoint C | 3
2016-05-30 | Sign Off | 1
Make beautiful timelines in PowerPoint for important meetings. |  |  |  | Download #1 Free timeline add-in for PowerPoint
www.officetimeline.com
Project Milestone Update
https://www.officetimeline.com/download
Note on D6: Project Timeline Tip: The position values vary the height of your Milestones and are used to prevent text overlap. Using negative numbers will place Milestones labels below the timeband. If you position a Milestone below the timeband click on its label in the chart to set its Label Position to below
Note on B17: Project Timeline Tip: To add more Milestones insert new rows into this table and then use the Select Data field to update your Series as show in step # 3 here: https://www.officetimeline.com/excel-timeline
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download Office Timeline Plus Edition for PowerPoint.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint. Copy your Excel table paste it into Office Timeline Plus.
3. Click the green check mark to instantly produce you timeline slide.